## Gantt Chart
Texting Legal Self-Help Project |  |  | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01
Milestone Phase | Category | Task
Phase 1 - Selecting Appropriate Technology
Evaluate & Assess Technology
Create Rubric for Evaluation | bar: 2022-01-01
Research Technologies for Texting Platform | bar: 2022-02-01
Assess Technologies Against Rubric | bar: 2022-03-01
Select Technology for Project | bar: 2022-03-01
Contract w/ Vendor
Draft Detailed Project Specifications | bar: 2022-04-01
Draft and Circulate Request for Proposals | bar: 2022-04-01
Evaluate Proposals and Select Vendor | bar: 2022-05-01
Hire Vendor | bar: 2022-06-01
Phase 2 - Pilot
Map User Journeys
Identify Categories of Advice/Brief Service | bar: 2022-07-01
Identify Endpoints | bar: 2022-07-01
Draft and Refine Texting Flows for Each Category and Endpoint | bar: 2022-08-01 to 2022-09-01
Build Pilot
Build Texting Flows in Technology | bar: 2022-10-01 to 2022-11-01
User Testing of Pilot | bar: 2022-11-01
Refine Pilot | bar: 2022-12-01
Phase 3 - Launch and Training
Launch
Launch Texting Program | bar: 2023-02-01
Conduct Community Outreach | bar: 2023-03-01 to 2023-06-01
Train
Train Administrative Users | bar: 2023-01-01
Create Instruction Manual for Administrative Users | bar: 2023-01-01